## Goal 1a
Goal 1. To create a climate of inclusivity at NSOE among students, staff, and faculty.
Objective 1a. All students, staff, and faculty will feel like they are a valued part of the NSOE Community
Activity | Group |  |  | Status | Score | Examples
| Student | Faculty | Staff
Communicate the formal and infomal routes for students, staff and faculty to address non-inclusive behavior | X | X | X | Developing | 2 | NSOE websites, MEM/MF orientation, DEI newsletter
Conduct staff, faculty and student meetings using the best practices of inclusive team process | X | X | X | Emerging | 1 | training provided to staff; best practices distributed to division chairs and ESP faculty
Provide mandatory anti-racism workshops to all incoming students, staff and faculty | X | X | X | Developing | 3 | anti-racism workshops are mandatory for all incoming MEM/MF students
Celebrate DEI success and activities in the Nic School | X | X | X | Developing | 2 | NSOE website, DEI newsletter
Ensure that all NSOE community members have voice in hiring high-level faculty and staff | X | X | X | Emerging | 1 | guidelines developed for inclusive search committees for faculty
Engage with and amplify BIPOC voices in the Durham community | X | X | X | Developing | 2 | DEEP Collaborative
Provide support for D&I related student groups | X | X | X | Transforming | 3 | funding provided to 3+ identity-based student groups
Offer regular undergraduate and graduate level workshop on academic skills, careers and discrimination | X | X | X | Transforming | 3 | workshops provided by NSOE Communications Studio, the CPDC, and the AD of DEI each year
Provide training on culturally inclusive teaching and course design to NSOE faculty |  | X |  | Transforming | 3 | inclusive pedagogy workshops and discussions offered to faculty at least once per semester
Give the CPDC resources to support undergraduates in career counseling and internship acquisition |  |  | X | No Effort | 0
Decolonize the curriculum by updating core courses to address systems of oppression | X | X |  | Emerging | 1 | AD of DEI is working with course instructor to address DEI issues identified in course evaluations
Create a vertically integrated undergraduate-graduate-alumni-faculty mentoring program | X | X |  | Developing | 2 | CAIRNS mentoring program, proposals in the works for PhD-post-doc-faculty programs
Facilitate an academic learning community and tutors for students enrolled in NSOE courses | X | X |  | Emerging | 1 | NSOE Communications Studio
Create opportunities for off-campus retreats to support URM students | X |  |  | No Effort | 0
Develop regular team-building activities to promote collaboration among faculty and staff |  | X | X | Emerging | 1 | Spring 2021 activities planned: faculty/staff workdays, all school Wednesday afternoon gathering, and faculty-staff led student pods
Create committee or assign the task of ensuring equitable distribution of service and tasks among faculty and staff |  | X | X | Emerging | 1 | faculty and staff have outlined roles and job descriptions
[5 empty] | 1.625 | Average Score

## Goal 1b
Goal 1. To create a climate of inclusivity at NSOE among students, staff, and faculty.
Objective 1b. All students, staff and faculty will feel like they are treated fairly.
Activity | Group |  |  | Status | Score | Examples
| Student | Faculty | Staff
Communicate resources to support students, staff and faculty in understanding and meeting DEI expectations | X | X | X | Emerging | 1 | DEI Implementation Plan, DEI Newsletter, DEI website
Evaluate division chairs regularly |  | X |  | Unknown | 0
Evaluate staff leaders regularly |  |  | X | Developing | 2 | Evaluations are provided, but historically have not included an explicit diversity critieria
Share & clarify expectations for faculty at different ranks regularly |  | X |  | Developing | 2 | Guidelines have been developed to clearly outline and delineate the roles of non-tenure track (NTT) faculty
Ensure that staff and faculty are evaluated annually by their supervisor or division chair |  | X | X | Developing | 2 | staff are evaluated annually; faculty in some divisions are given annual feedback
Ensure that course evaluations address fair treatment and culturally inclusive teaching practices, and that problems are addressed | X | X |  | Transforming | 3 | course evalutions explicit include DEI critieria and the AD of DEI addresses DEI concerns individually with faculty each semester
Conduct regular syllabus reviews to ensure equity in teaching practices | X | X |  | Emerging | 1 | This has been discussed with the SADs and is in development
[5 empty] | 1.5714 | Average Score

## Goal 2a
Goal 2. To attract and successfully recruit students, staff and faculty from all backgrounds to NSOE
Objective 2a. The Nicholas School uses practices that support the recruitment and retention of staff and faculty from a variety of backgrounds
Activity | Group |  | Status | Score | Examples
| Faculty | Staff
Establish practices that ensure equity in the selection and hiring of staff and faculty | X | X | Emerging | 1 | Equitable hiring practice guidelines have been created, including requirements for search committee members to have implicit bias training and meet with the AD of DEI during search processes for faculty
Prioritize diversity, equity and inclusion in staff, faculty and dean-level hiring | X | X | Developing | 2 | This has been a stated goal of strategic plans since at least 2016 and a stated goal of NSOE since it's inception; some DEI best practices have been used in searches for the last several years
Create a comprehensive NSOE D&I Online Toolkit with a compilation of resources and best hiring practices that ensure equity in the selection and hiring of staff and faculty | X | X | Emerging | 1 | A comprehensive toolkit has been created for faculty hires, rolling out in January 2022
Add values statements to job advertisements | X | X | Transforming | 3 | This is a standard part of job and faculty search advertisements
Appoint women and URM faculty/staff to search committees | X | X | No effort | 0
Provide visible opportunities for leadership from staff and faculty from historically marginalized communities | X | X | Emerging | 1 | Opportunities are available, but not with explicit cultivation of leadershpi from historically marginalized groups
Establish a set of practices that ensure the advancement and growth of each faculty and staff member | X | X | Emerging | 1 | Workshops for Spring 2021 are in development for staff leaders on this topic
Use cluster hires to recruit faculty from under-represented backgrounds | X |  | Emerging | 1 | This has been attempted in that several hires often happen at the same time, but not explicit clustering hiring has been prioritized
Develop a visitor/sabbatical host program targeting URM faculty working in areas that intersect environmental sciences and major research initiatives at Duke | X |  | No effort | 0
Develop a prestigious postdoctoral fellows program that brings minority scholars to campus | X |  | No effort | 0
Designate a faculty diversity chair | X |  | No effort | 0
Promote collaborative engagement among faculty | X |  | Developing | 2 | Dean's funding requests explicitly seek to support interdisciplinary collaboration among Nicholas School faculty
Provide financial support for all assistant professors to build networks with other academics and practitioners internal and external to NSOE | X |  | Emerging | 1 | Tenure track faculty are given some initial start up funds, this is subject to closed-door negotiations
Show support for faculty research involving the populations with which they identify | X |  | Developing | 2 | Dean Newsletter and DEI Newsletter celebrates this work
|  |  |  | 1.0714 | Average Score

## Goal 2b
Goal 2. To attract and successfully recruit students, staff and faculty from all backgrounds to NSOE
Objective 2b. The Nicholas School uses practices that support the recruitment and retention of students from a variety of backgrounds
Activity | Group |  | Status | Score | Examples
| Faculty | Staff
Recruit students from college and diversity fairs | X | X | Transforming | 3 | This has been standard in the Nicholas School for at least 5 years
Recruit students into MEM program from HBCUs and minority-serving institutions | X | X | Emerging | 1 | Some work has been done with HBCUs, but this work lost momentum during the COVID 19 pandemic
Start chapters for professional societies with programming geared towards increaing racial and other diversity in environmental sciences | X |  | No effort | 0
Provide paid research experiences for students in the Nicholas School | X |  | Developing | 2 | Paid work experiences are available though assistantships, jobs at the Nicholas Institute, and through the internship program
Expand the number of cross-listed NSOE courses (including Writing 101 and first year seminars) and minimize conflicts with popular and required courses both within and outside of NSOE | X |  | Developing | 2 | Efforts are made to minimize conflicts among required and popular courses, especially for the MEM/MF program
Make more classes available on the Durham campus over the summer | X |  | Developing | 2 | The SADs send out call for summer class proposals from faculty each year
Show how NSOE's curriculum is directly relevant to careers in the environment | X |  | Developing | 2 | This is done in program advertising, through some program area seminars, and in some individual classes
Offer additional concentrations (e.g., environmental education, climate change, environmental justice, and ecology) | X |  | Emerging | 1 | additional certificates have been added in recent years and discussions have been had about additional or different concentrations
Develop pre-Freshman year summer bridge program | X |  | No effort | 0 | the Nicholas School does not have access to students until they declare a major
Develop a professional school boot camp program | X |  | Emerging | 1 | professional bootcamps are currently being discussed in the MEM/MF curriculum strategic planning process that is on-going
Continue K-12 outreach programs | X |  | Transforming | 3 | AHEAD (merged from ESSP, HackBio, bioSTEM), community science program at DUML, and ELEMENT are on-going
Connect the K-12 programs to the vertically integrated mentoring programs for Duke students and faculty | X |  | Transforming | 3 | AHEAD (merged from ESSP, HackBio, bioSTEM), community science program at DUML, and ELEMENT are on-going
Train high school guidance counselors about environmental careers | X |  | Emerging | 1 | This was tentatively planned prior to the pandemic
Train and encourage faculty to use culturally inclusive pedagogy techniques | X |  | Transforming | 3 | in 2020 all faculty were required to attend an inclusive pedagogy workshop, workshops have been offered on this topic each semester following
Integrate Environmental Justice into the curriculum | X |  | Emerging | 1 | environmental justice has been taught by an external instructor for the past several years
Review the admissions and enrollment process for bias, clarity and efficiency |  | X | Developing | 2 | these processes have been reviewed but additional review and revision is needed
Require staff members involved in admissions to complete the implicit bias training |  | X | Transforming | 3 | all application readers engage in implicit bias training inteograted into the application reader training
Remove the GRE requirement for graduate student applicants |  | X | Developing | 2 | for the last two admissions cycles this GRE requirement has been removed
Establish scholarship funds for students from underrepresented backgrounds |  | X | Transforming | 3 | scholarship funds are available for students from a diversity of backgrounds, within the confines of US laws and regulations
Waive application fees for low-income students |  | X | Developing | 2 | applications fees have been waived during the last admissions cycle
Strengthen financial support systems for NSOE students |  | X | Developing | 2 | work has been done to increase the number of scholarship opportunities and the endowment for scholarships for professional students in particular
Send out lists of available courses each semester to all students |  | X | Transforming | 3 | the MEM newsletter provides reminders on courses and this information is also available via DukeHub
Share NSOE opportunities for undergraduates outside of NSOE, including work-study opportunities |  | X | Emerging | 1 | opportunities are shared regularly with CAIRNS students and sometimes through student networks like the UEU and Sustainable Duke
Increase advertisement of 3+2 degree program, minors and certificates with first-year students |  | X | Emerging | 1 | the number of certificate programs has increased in recent years
Use preferred student media to advertise to students |  | X | Developing | 2 | surveys have been done about preferred media and these techniques are being used in some venues
Open NSOE's Career and Professional Development Center to undergraduate students |  | X | No effort | 0
Showcase lucrative career opportunities available with NSOE degree |  | X | Developing | 2 | This work is often done by the CPDC or through undergraduate mentoring programs, like the CAIRNS program
|  |  |  | 1.7778 | Average Score